## TIMELINE
To avoid unnecessary delays and port fees, cargo must be cleard as quickly as possible. The template below illustrates the many tasks involved in clearance that must be completed.
| 1. | Clearance requirements vary by country and commodity. This template must be modified to conform to specific requirements and conditions.
| 2. | Complete the modified template with a "Date" for each task completion.
| 3. | Assign responsibility for each task, emphasizing the need to complete the tasks by that date.
NOTES:
On a TB/L the shipping company will normally arrange export clearance.
In some cases, fumigation may be conducted on the vessel before commodity can be discharged.
If there are problems with customs clearance, obtain a bonded warehouse or bank guarantee, and port authorization.
ACTIVITY |  |  |  |  | Minimum # of Days | Date
Shipment departure from U.S.
Shipment arrival at discharge port
Period of free days allowed in port (not including fumigation time)
Containers to be returned empty to shipping company (if applicable)
4. | RELEASE FROM SHIPPING COMPANY
Release from shipping company requires:
Send release letter to shipping company.
Shipping company releases cargo.
3.1 (Vessel in Port) |  | CUSTOMS CLEARANCE
(Agriculture authorities) inspects for infestation and documents results.
(Health authorities) inspects and sample commodities and document results.
Pay port fees.
Process bills of entry (including request for customs clearance).
Request includes:
Obtain customs clearance.
3.2 (Vessel in Port) |  | (Other activities after vessel arrives in port)
2.1 (Vessel sailed from U.S. Port) |  |  | EXEMPTION FROM IMPORT TAXES
Receive bill of lading.
Request support letter from (government agency granting agency legal status)
Submit (to government agency) request for GMO certification.
Request in following documents:
(Government agency) issues GMO certification.
Submit (to Agriculture authorities) request for certification.
(Agriculture authorities) issues certification.
Apply for import permit.
Obtain import permit.
Apply for duty-free letter.
Obtain duty-free letter.
Forward all documents to the C&F Agent.
1.1 (Vessel loading in U.S.) |  |  |  | PREPARATION
Booking Note received.
Alert (government officials) as to vessel arrival date.
Identify individuals to contact for clearances.