## Dataflow Map
Multipurpose Cash Assistance Programmatic Dataflow Map
# | Task | Description | Who leads? | Who is involved? | What data is being collected? | How is the data used? | When does it usually take place? | Standard tools/ resources
1 | Client/Feedback Responsive Mechanisms (CRM/FRM) | The purpose of Client Responsiveness Mechanisms is to ensure that clients' perspectives are captured for use in identifying issues (especially related to service quality) during project implementation, and to inform coure corrections. Typical client responsiveness mechanisms for cash can include: - Feedback registry - Community feedback committees - Suggestion box - Phone hotline - Whatsapp hotline / facebook groups (where applicable) - Focus group discussions | MEAL team or Accountability Team, if applicable | All clients | Client feedback | To improve programming by identifying, responding, and adapting to participant concerns and feedback about the project. | - CFM should be set-up at the earliest possible opportunity so it is available to clients throughout the project. - Client feedback is collected continuously throughout the project - Feedback mechanism should be publicized/referenced any time project staff are in contact with clients | Client feedback mechanism resources
2 | Market Price Monitoring | Market monitoring involves tracking general trends and market prices for staple food items and key non-food items (NFIs) that compromise the Minimum Expenditure Basket (MEB) in areas where cash programming is being implemented. Since the MEB is typically used to determine cash transfer values, market monitoring allows the program to identify price changes that may necessitate changes to the transfer value , as well to identify price inflation caused by cash assistance (for large scale cash projects). Before setting up market monitoring by your project/ organization, check the availability of up-to-date market data from 3rd party sources such as: Cash Working Group, Food Security Cluster, or REACH's Joint Market Monitoring Initiative (JMMI). Note: Only set up market price monitoring processes if accurate and up-to-date data is not already available through 3rd party sources. | MEAL team | Traders in local markets | Market price data and information on market trends | To set and adjust cash transfer values to changing market prices as needed, and to identify and address inflation or other market challenges that impact programming. | - Market monitoring should be established prior to beginning cash distributions - Markret monitoring data should be collected on a weekly, biweekly or monthly basis (context dependent) for the full duration of the cash distributions | Market Monitoring (MarKit 2.0) Market Price Monitoring Tool (XLSform) + 1-pager
3 | Initial community sensitization | Meeting with community members and leaders to explain and validate the following: (a) project activities/purpose (b) timeline for implementation of the project (c) Client Responsiveness mechanisms (d) target population and client eligibility/ selection criteria, (e) to determine who will serve on any required community-level committees (ex: complaints committee) | Program team | All clients | N/A | N/A | Typically several days before registration occurs in the relevant community | N/A
4 | Client registration / identification | The process of registering clients/households to participate in the cash program. There are two common approaches: (a) Targeted registration: only people/households who have been selected to receive assistance are registered (b) Blanket registration: a more comprehensive registration of vulnerable people is conducted, from which a sub-group of clients are subsequently selected. | Program team | All clients | client biodata client household information Vulnerability / eligibility criteria data | To establish an initial list of potential project clients which contains the personal and household-level data needed to confirm their identity and eligilibity for assistance. | Appx 2 weeks before the 1st distribution is expected to occur (to allow time for client verification and the baseline survey) | Example of registration form
5 | Client Validation/ Verification | The purpose of verification is two-fold: (a) confirming the accuracy of client list by conducting a data quality review of the client list and spot-checking the key biodata - typically by phone with ~5% of clients (b) Validating that the clients meet the eligibility / vulnerability requirements of the project. This is often done through applying a vulnerability criteria/scoring formula. | M&E team | All clients or a sample of 5-10% (at discretion of program management) | Confirmation of biodata and household information of clients Vulnerability scores Final/validated list | To validate the accuracy of the client registration list, and verify the consistency/fairness of the registration process | In the week after registration | Example of vulnerability scoring
6 | Baseline survey | The purpose of the baseline survey is to capture the relevant outcome-level indicators and other relevant socioeconomic data of the clients before the cash distributions begin, to compare with endline data captured after the distributions and determine the outcomes of the project. | M&E team | Representative sample of clients | client biodata client household information Outcome Indicators | To establish the situation of clients prior to receiving assistance from the project, with respect to the key outcome-level indicators being tracked by the project. | (a) Ideally 1-2 weeks before the 1st distribution or; (b) During client registration: but this can result in a lengthy registration process, and if there is a time lag between registration and distribution the data may be out of date or; (c) On the day of the first distribution: but this is logistically complicated to organize and not recommended unless there is no other option. | Cash Baseline/Endline Survey Sampling guidance
7 | Distributions | 1st round of cash distributions/payments to the clients. On the day of the distribution. Client feedback mechanisms should be available: (a) Designated member of staff to report issues to (b) Suggestion box / hotline (c) Exit surveys: some programs implement quick exit surveys as a spot-check for issues with about 5% of clients (d) Distribution Site monitoring: a monitoring form completed by M&E staff that capture any observations about the distribution process (may not be applicable when using digital payment mechanisms) | Program team + M&E team | All clients | Payment records Exit survey results Site monitoring form | To record key data on all distributions made for financial compliance, output reporting, and assessing the quality of the distribution process | 1st distribution: as soon as possible after the baseline survey Subsequent distributions: typically 30 days apart | N/A
8 | Post Distribution Monitoring (PDM) | The purpose of the PDM survey is to actively capture client feedback and satisfaction with cash programming and check for commo program process / quality issues. * Note: most projects conduct PDM after every round of distributions, however if the project involves 4 or more months of distributions to the same clients, PDMs are sometimes done every other distribution to minimize cost. (For example: conducting PDMs after the 1st round, 3rd round, 5th round...) | M&E team | Representative sample of clients | client biodata client satisfaction and feedback Program process / quality data | To proactively solicit more in-depth feedback from clients about the processes of selection, distribution and spending of cash assistance. | 2-3 weeks after each distribution | Cash PDM tool Sampling guidance
9 | Pause and reflect meetings / discussions | The purpose of pause and reflect meetings is to bring together MEAL, cash technical, and program managers together to discuss the monitoring data and identify patterns and potential changes that need to be made to program design. | Program team + M&E team | Program managers, cash technical, and M&E staff | N/A | The discussion should inform changes to program design. | It depends on the program. But a good option is after the first PDM and at least quarterly thereafter. Data sources can include PDMs, market monitoring data, baseline data, qualitative observations, and more. | https://usaidlearninglab.org/qrg/pause-and-reflect
10 | Endline survey | The purpose of the endline survey is to capture the relevant Outcome Indicators and other relevant socioeconomic data of the clients before the cash distributions begin, to compare with baseline data captured before the distributions and determine the outcomes of the project. * Note: projects will often combine the Endline survey with the final round of PDMs to save time and cost of multiple client surveys within the same time period | M&E team | Representative sample of clients | client biodata client household information Outcome Indicators | To follow-up on the situation of clients after receiving assistance from the project, with respect to the key outcome-level indicators being tracked by the project. | 2-4 weeks after the final distribution | Cash Baseline/Endline Survey Sampling guidance