## Slide 1
Refinement Year 1
Year 5
Year 5
Year 6
Award application based on:
a sound ToC,
innovative strategies
significant promise to sustainably improve the food & nutrition security of vulnerable populations
ambitious targets
knowledge about target areas
built in sustainability strategy
Validate/ refine the TOC and strategies
based on:
Community engagement and consultation
Comprehensive gender analysis
Environmental analysis
Barrier analysis,
Sustainability analysis
Baseline survey results
Interim external evaluation
Quantitative and qualitative
Closeout
Extension plan with revised targets
Up to 3 to 5 years
M&E Workshop
Presentation
FY 16 Refine and Implement
Implementation
Year 2 to 4

## Slide 2
FY 16 Refine and Implement
What should the refinement stage look like?

## Slide 3
FY 16 Refine and Implement
Year 1
Year 2
Year 3
Year 4
Application Submission, TEC Review and
Award
(5yrs w/ options)
Activities
Timeline
Milestones
Refinement Stage

## Slide 4
FY 16 Refine and Implement
Activities (Awardee) – first six months
  Review and refine geographic targeting at the community level
  Provide a list of communities to FFP within the first three months
  Community consultations and validation of assumptions
    Discuss priorities and needs, causes of food insecurity and under nutrition, vulnerability to food insecurity and malnutrition shocks, capacity and strengths to recover from food insecurity shocks
  Institutional analysis and validation of operating environment and policies
    Institutional and policy environment
    Governance issues
    Synergies with other USG investments
    Linkages to achieve broader resilience objectives

## Slide 5
FY 16 Refine and Implement
Activities (Awardee) – first six months, continued
Formative research - examples may include:
    Barriers to optimum health/nutrition practices for pregnant/lactating mothers and children under two
    Barriers to hygiene practices, sanitation practices and access to safe water
    Barriers to improved agricultural practices, factors that limit access to increased income
    Barriers to recovery from food insecurity shocks
    Climate and water resources vulnerability analysis
Gender analysis – required
Value chain analysis (for projects that promote value chain)
Market analysis (for targeted commodities)
Initial Environment Examination (IEE)- required
Major shocks and stresses and how people are managing them

## Slide 6
FY 16 Refine and Implement
Activities (FFP) – first six months, continued
AOR reviews and approves plans
Scoping visit by the FFP technical team members with the awardee technical staff
TEC team reviews and approves scopes of work for various studies and assessments (FFP will provide comments within approximately three weeks)
AOR/ Activity Managers and TEC team members closely monitor activities
Baseline study – required (results should be available to the partner within nine to ten months of kick off date)
    Baseline study collects data for high level outcome and impact indicators from FFP list and awardee’s list
    Note: Baseline data for lower level outcome indicators can be collected from beneficiaries as a part of annual monitoring.
Notes: Awardee Technical Staff – in second bullet – when you present, you might want to flag that staff hiring can’t wait until end of refinement period.

## Slide 7
FY 16 Refine and Implement
  Activities (Awardee) – months seven to twelve
  Review and possible refinement of theory of change and the project strategies in light of the baseline results and other studies
  Develop M&E plan, including Gender and Environment
  Finalize targets
  Establish partnerships with Feed the Future, Global Climate Change and other projects with benchmarks
  Staff training
  The Chief of Party/Head of the Project will make a presentation of the refined project design highlighting changes from original and reasons why

## Slide 8
FY 16 Refine and Implement
Activities (FFP) – months seven to twelve, continued
  Review reports of various studies
  Organize and facilitate M&E workshop to refine LogFrame and IPTT with Gender and Environment issues
  Review targets
  Review baseline study report
  Provide oversight to the baseline contractor

## Slide 9
FY 16 Refine and Implement
Milestones
  Scopes of work for various studies submitted.
  List of communities submitted to the baseline study contractor.
  Reports for different studies submitted to FFP.
  Refined theory of change and LogFrame submitted.
  Partnership plans with benchmarks submitted
  Targets revised and submitted
  Adjusted staffing plan submitted